## Sheet1
Stand up meeting date: 18/ 12/ 2023
Team's name | Group 03
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Chen | Add feature Remove product | 1 h | 1 h | Design slide | 1 h
Thida him | Edit template for add product | 1 h | 1 h | Design slide | 1 h
senghak chhun | Add product in page product(go on) | 2 h | 1 h | Checkout Product | 2 h