## 19
Stand up meeting date: 19/ 02/ 2024
Team's name | Group 04 E-classroom
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
senghak chhun | create sign in feature | 4 h | 10 h | create classroom | 3h
rady doeurn | sigup interface | 1 h40m | 3h | search js full calendar | 4h
theun en | create home page after create account | 2h 20m | 1d | delete classroom | 1h 42m
sreymon chak | create general page before create account | 2h 20m | 11h | review code | 4h
sreynang rith | create login page | 1h 40m | 2h30mn | update account | 2h 30m

## 23
Stand up meeting date: 23/ 02/ 2024
Team's name | Group 04 E-classroom
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
senghak chhun | create classroom | 3h | 3h 20m | fix bug sign up | 4h
rady doeurn | make js full calendar | 4h | go on | interface for classroom | 6h
theun en | delete classroom | 1h 42m | 1d | achieve class | 4h
sreymon chak | review code | 4h | 4h | display teacher in classroom | 3h 20m
sreynang rith | update account | 2h 30m | go on | update account | 4h